## 시트1
ADSOFT 신입사원 교육과정
단계 |  | 세부내용 |  |  | 10월 | [19 empty] | 11월 | [20 empty] | 12월
|  | 매주 월요일 오후 2시 발표 |  |  | 1주차 |  |  |  |  | 2주차 |  |  |  |  | 3주차 |  |  |  |  | 4주차 |  |  |  |  | 5주차 |  |  |  |  | 6주차 |  |  |  |  | 7주차 |  |  |  |  | 8주차 |  |  |  |  | 9주차 |  |  |  |  | 10주차 |  |  |  |  | 11주차 |  |  |  |  | 12주차 |  |  |  |  | 13주차
|  |  | 완성도 | 추가/보완 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 30 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 31 | 1
기초교육 | 1 | 웹 서버, 웹 어플리케이션 서버 차이 (과거, 현재, 미래) | 100 | PPT 가독성 | bar: 1주차 5 to 1주차 9
| 2 | HTTP 분석 (패킷구조), HTTP 헤더 분석 (HttpRequest, HttpResponse 위주로 분석), HTTP/HTTPS 보안상 차이 (스니핑) | 100 | SSL, TLS 인증서 관련 상세 내용 | bar: 2주차 12 to 2주차 16
| 3 | tcp/ip 4계층과 http 프로토콜 차이, AJAX란 | 100 | TCP, UDP 의 패킷 순서 관련 내용 | bar: 3주차 19 to 3주차 23
git 사용방법 - local repository, remote repository - fetch, pull, commit, push, merge 종류 등 | bar: 3주차 19 to 3주차 23
| 4 | MVC패턴과 자바에서 실제 사용되는 예 (어떤파일들이 각각에 해당되는지 등), SPA, PWA(progressive web app)비교/차이 | 0 | bar: 4주차 26 to 4주차 30
| 5 | DB테이블 설계 (정규화 4단계와 반정규화), 사용자 계정(로그인)기능 중 세션, 토큰 방식 차이(JWT) 만료 연장 방법 (슬라이딩 세션 등 그외) | 0 | bar: 5주차 2 to 5주차 6
실무교육 | 6 | REST API 란? (백엔드) - asp.net core 3.1 web api + MyBatis.NET 프로젝트로 구현해보기 | 0 | bar: 6주차 9 to 7주차 20
| 7 | Vue.js 란? (프론트엔드) - 스터디 +배포까지, node js 와 npm 개념 (node js는 간략히) +책 Vuex 추가 ES5, ES6 기준 비교차이 + JS import/export 방식, aync, await 개념, push 서버 개념, SignalR 개념, websocket 개념(웹표준은 생략) | 0 | bar: 8주차 23 to 11주차 18
| 8 | DevExpress 데이터 테이블 - 스터디 + 샘플 화면 구현 | 0 | bar: 12주차 21 to 13주차 1
Note on D6: 참고자료 https://hackersstudy.tistory.com/16 https://sleepyeyes.tistory.com/13 https://deftkang.tistory.com/104?category=1089010 https://my-repo.tistory.com/20 https://history1994.tistory.com/7 http://libqa.com/wiki/132 https://deftkang.tistory.com/21 https://www.itfind.or.kr/UGAN/NIPA/WAS%20%ec%86%94%eb%a3%a8%ec%85%98%20%ec%8b%9c%ec%9e%a5%20%eb%8f%99%ed%96%a5.pdf https://gmlwjd9405.github.io/2018/10/27/webserver-vs-was.html https://www.slideshare.net/JinKyoungHeo/1-53043728
Note on D7: 참고자료 https://www.zerocho.com/category/HTTP/post/5b3ba2d0b3dabd001b53b9db https://medium.com/@chrisjune_13837/web-http-tcp-ip-%EB%A9%94%EC%8B%9C%EC%A7%80%EB%9E%80-4b2721fe296f http://blog.wishket.com/http-vs-https-%EC%B0%A8%EC%9D%B4-%EC%95%8C%EB%A9%B4-%EC%82%AC%EC%9D%B4%ED%8A%B8%EC%9D%98-%EB%A0%88%EB%B2%A8%EC%9D%B4-%EB%B3%B4%EC%9D%B8%EB%8B%A4/ https://velog.io/@ddinggu/HTML-DOM-%EA%B0%84%EB%8B%A8-%EC%A0%95%EB%A6%AC https://kamang-it.tistory.com/entry/Web%EB%8F%99%EC%9D%BC-%EC%B6%9C%EC%B2%98-%EC%A0%95%EC%B1%85-CORS-%EB%8F%84%EB%8C%80%EC%B2%B4-%EB%AD%98%EA%B9%8C https://m.blog.naver.com/PostView.nhn?blogId=s2kiess&logNo=30182409370&proxyReferer=https:%2F%2Fwww.google.com%2F http://blog.naver.com/skinfosec2000/220601267742
Note on D8: https://asec.ahnlab.com/156 https://mangkyu.tistory.com/15 https://seolhun.github.io/contents/network-http-http-vs-https%EC%9D%98-%EC%B0%A8%EC%9D%B4-%EA%B7%B8%EB%A6%AC%EA%B3%A0-packet%EA%B3%BC-tsl-ssl https://shlee0882.tistory.com/110 https://feel5ny.github.io/2019/08/26/HTTP_004_01/ http://tlog.tammolo.com/blog/4-cf6edc94-2ac1-4b59-b7bd-99b5fbb00287/ ip IP https://m.blog.naver.com/PostView.nhn?blogId=nackji80&logNo=220486253904&proxyReferer=https:%2F%2Fwww.google.com%2F ajax https://velog.io/@johnque/AJAX%EB%9E%80 https://hieroglyph.tistory.com/13 https://coding-factory.tistory.com/143?category=785989 http://www.ktword.co.kr/abbr_view.php?m_temp1=5939&id=1382 http://tcpschool.com/xml/xml_basic_element https://git-scm.com/book/ko/v2/Git-%EC%84%9C%EB%B2%84-%EC%84%9C%EB%B2%84%EC%97%90-Git-%EC%84%A4%EC%B9%98%ED%95%98%EA%B8%B0 https://parksb.github.io/article/28.html https://git-scm.com/book/ko/v2/Git-%EB%B8%8C%EB%9E%9C%EC%B9%98-%EB%A6%AC%EB%AA%A8%ED%8A%B8-%EB%B8%8C%EB%9E%9C%EC%B9%98 동영상 https://opentutorials.org/course/2708/15210 https://git-scm.com/book/ko/v2/%EC%8B%9C%EC%9E%91%ED%95%98%EA%B8%B0-Git-%EA%B8%B0%EC%B4%88 https://velog.io/@ybear90/Git%EC%9D%84-%EC%82%AC%EC%9A%A9%ED%95%98%EA%B8%B0-%EC%9C%84%ED%95%9C-%EA%B8%B0%EC%B4%88-%EC%A0%95%EB%A6%AC-1 https://coding-groot.tistory.com/111 https://velog.io/@yejikang/Git%EC%9D%B4%EB%9E%80 https://flowerykeyboard.tistory.com/9 https://medium.com/asciiart/git-%EC%9B%90%EB%A6%AC-%EC%A0%95%EB%A6%AC-%EB%B0%8F-%EA%B4%80%EB%A0%A8-%EB%A7%81%ED%81%AC%EB%93%A4-2a7c8a00cdcb https://medium.com/happyprogrammer-in-jeju/git-%EB%82%B4%EB%B6%80-%EA%B5%AC%EC%A1%B0%EB%A5%BC-%EC%95%8C%EC%95%84%EB%B3%B4%EC%9E%90-1-%EA%B8%B0%EB%B3%B8-%EC%98%A4%EB%B8%8C%EC%A0%9D%ED%8A%B8-81b34f85fe53

## 설문지 응답 시트1
타임스탬프 | 제목없는 질문